## START
Click here to enter a new item to your Genebank Risk Management REGISTER

## RiskRegister
RISK ID | GENERAL AREA : Activity | Risk Source | Consequence 1 | Consequence 2 | Consequence 3 | Consequence 4 | Consequence 5 | Risk Owner | Likelihood Level | Germplasm | Information | People | Environment | Asset/Facility | operations | Legal | Reputation | Adjustment Factor | Adjustment Factor DESCRIPTION | Risk Rating | Risk Level

## RiskManagement
RISK ID | GENERAL AREA : Activity | Risk Source | Risk Owner | Risk Level | Action Plan: People | Action Plan: Facility | Action Plan: Procedure | Contingency

## LISTs (hidden)
Acquisition: Collecting | Acquisition: Donation | Conservation: Registration | Conservation: Sample Processing | Conservation: Storage | Conservation: Testing | Conservation: Regeneration | Conservation: Characterization and Evaluation | Distribution: Policies | Distribution: Seed or Explant Preparation | Distribution: Dispatch | Information Management and Dissemination: Labelling | Information Management and Dissemination: Data Handling | Information Management and Dissemination: Back-up | Information Management and Dissemination: Data Quality | Information Management and Dissemination: Data Sharing | Infrastructure / Physical Facility: Functionality | Infrastructure / Physical Facility: Security | Personnel and Support Services: Personnel | Personnel and Support Services: Working environment | Personnel and Support Services: Support Services | Personnel and Support Services: Financial | 1 |  | Acquisition: Collecting | Narrow genetic variability and large gaps in germplasm collection | Failure to capture diversity in field | Send Center genebank personnel to take the lead in joint collecting missions with national programs. Conduct training of collectors in partner countries. Maintain and hire a pool of expert collectors. |  | Analyse collection for un-represented regions and conduct gap-filling collecting. | Send a follow-up collecting mission. | GRU | Consequence
Narrow genetic variability and large gaps in germplasm collection | Received foreign materials carry pests and diseases | Unverified passport and other data submitted | Culling of perceived offtypes that are true components of original sample | Misplacement of packets back into storage tray during briefings to visitors | Human error in taking and encoding weight readings | Poor field plot management | Inefficient and erroneous data gathering and encoding | Lack of knowledge or negligence on seed exchange Protocol and International Treaty | Misclassification and wrong characterization and seed stocks data | Germplasm distributed with low viability | Fading of labels and mislabelling of new bags and other containers for the germplasm accession | Inefficient recording and database management | Lack of secure back-up | Inaccurate location of collecting sites | Slow availability of evaluation data for international users | Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests) | Power supply cut-off | Inadequate complement of technical staff | Routine tasks and uncompetitive remuneration | Inefficient human resources services | High cost of genebank operations | 2 |  |  | Narrow genetic variability and large gaps in germplasm collection | [6 empty] | People
Wide variability in flowering time and high shattering of wild types | Limited seed testing capability | Received materials have low viability | Non-removal of damaged seeds hence reducing true viable sample size | Underestimate of critical sample size | Defective weighing apparatus | Misidentification of accessions | Descriptors that have no clear-cut correspondence to current international standard descriptors | Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm | Inefficient and slow processing of requests for samples. | Loss of documentation | Misplacement of labels as seeds are laid out for drying | Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation) |  | Inadequate information about important traits of accessions. | Limited ICT capability; server, network and IT related problems | Poor organization of storage trays, shelves and compartments | Theft or vandalism | Incompetent staff | Exposure to occupational hazards | Inefficient purchasing and repair services | Late release of project funds | 3 |  |  | Narrow genetic variability and large gaps in germplasm collection | [6 empty] | Facility
Low seed amount of new acquisitions | Reluctance to share germplasm due to IP rights |  | Inefficient fumigation | Ineffective packaging material and method permeable to moisture, pest or pathogen | Inefficient conduct of viability test and encoding | Mis-roguing of true components of original germplasm | Limited text-based description | Non-compliance with phytosanitary regulations | Errors in preparing or labeling samples | Unfavorable conditions during transport |  | Improper recording of moisture content, seed inventory, viability, storage location, and characterization data. |  | Human error in data gathering | Malfunctioning equipment, hardware and software problems, and power interruption | Deterioration of facilities and equipment | Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire |  | ergonomics/functionality of laboratory furnitures (design flaws, equipment bought not to specification, etc) | Assigning manpower that are not trained for genebank work |  | Low |  |  | Narrow genetic variability and large gaps in germplasm collection | [6 empty] | Procedure
Untrained personnel in collecting and documentation | Working collections not duplicated in major genebanks |  | Lack of proper disposal procedures for contaminated plant materials | Safety duplication site is vulnerable to natural calamities | Human error in viability evaluation. | Differential pollen productivity of subtypes in highly heterogenous samples. | Lack of diversity assessment of collection |  | Insufficient seed stock for distribution |  |  |  |  | Important data and information remain in unuseful form. |  | Cold room malfunction | [5 empty] | Medium |  |  | Narrow genetic variability and large gaps in germplasm collection | [6 empty] | Contingency
Misidentification of germplasm | Donated seeds carrying seed-borne pests and other pathogens |  | Mixture from unclean mechanical threshers and selection of hardy grains resistant to mechanical threshers | Changing policies, financial and technical capabilities of governments hosting safety duplication | Dormancy | Cross pollination from other germplasm | [15 empty] | High |  |  | Narrow genetic variability and large gaps in germplasm collection | [6 empty] | Responsible Unit
Lack of simple collection protocol and documentation forms |  |  | Body parts coming in contact with hot components, moving parts, unguarded machines, and sharp objects during harvesting, threshing, oven drying or packaging of samples. | Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests) | Unsuitable viability testing procedure for special types of germplasm | Suboptimal pollination | [18 empty] | Narrow genetic variability and large gaps in germplasm collection
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events |  |  | Exposure to allergens (dust, trichomes, insect bites and other airborne irritants) from samples being processed | Poor organization of storage trays, shelves and compartments | Inappropriate viability testing interval | Poor quality of harvest for storage | [18 empty] | Narrow genetic variability and large gaps in germplasm collection
Strict country and international laws on access and use of germplasm |  |  | Improper posture due to prolonged sitting or standing | Deterioration of facilities and equipment | Human error in seed health evaluation. | Different regeneration environment from the site of origin | [16 empty] | 0 |  | Narrow genetic variability and large gaps in germplasm collection
Breach of country and international treaties |  |  | Inadequate or improper illumination during seed cleaning | Cold room malfunction | Improper pest screening methods | Inappropriate location of genebank for regeneration of photoperiod-sensitive materials | [16 empty] | 1 |  | Narrow genetic variability and large gaps in germplasm collection
Ambiguous position of countries regarding international treaties |  |  | Exposure to microscopic particulates during reactivation of silica gel dessicant | Power supply cut-off | Defective pest screening equipment | Escape of non-native species into environment | [16 empty] | 1 |  | Wide variability in flowering time and high shattering of wild types | Failure to capture diversity in field |  |  | Collect large amount of original sample. | Send a follow-up collecting mission. | GRU
Exposure to crime-related events during collection trips |  |  |  | Theft or vandalism | Untrained personnel in transgene detection | Endemic diseases from adjacent production areas | [16 empty] | 0
Exposure to natural disasters during collection trips |  |  |  | Exposure to falling jars or boxes while stocking seed samples for storage | Lack or improper determination of transgene presence | Unavailability of pesticides to control major insect pests due to strict regulations
Exposure to road hazards and poor travel conditions |  |  |  | Exposure of personnel to extreme temperature changes during storage processes (stocking of samples in the cold chambers, etc.) or from being accidentally trapped in the cold rooms. | Inadvertent spread of transgene in the collection | Low germination of germplasm due to strong dormancy
Personnel becoming lost or hurt due to unfamiliarity to place, customs, local dialects in area of collection |  |  |  | Exposure to sharp awns and trichomes during viability scoring
Exposure to dangerous animal bites, exotic diseases and viral infections that may be common to the collection site such as SARS, A(H1N1), malaria, dengue, measles, rabies, etc.
[25 empty] | Low seed amount of new acquisitions | Genetic drift |  |  | Collect large amount of original sample. | Send a follow-up collecting mission. | GRU
Low seed amount of new acquisitions
Low seed amount of new acquisitions
Low seed amount of new acquisitions
Low seed amount of new acquisitions
Low seed amount of new acquisitions
Low seed amount of new acquisitions
Low seed amount of new acquisitions
Low seed amount of new acquisitions
Low seed amount of new acquisitions
[25 empty] | Untrained personnel in collecting and documentation | Failure to capture diversity in field and document important information | Send Center genebank personnel to take the lead in joint collecting missions with national programs. Conduct training of collectors in partner countries. Maintain and hire a pool of expert collectors. |  |  | Send a follow-up collecting mission. | GRU
Untrained personnel in collecting and documentation
Untrained personnel in collecting and documentation
Untrained personnel in collecting and documentation
Untrained personnel in collecting and documentation
Untrained personnel in collecting and documentation
Untrained personnel in collecting and documentation
Untrained personnel in collecting and documentation
Untrained personnel in collecting and documentation
Untrained personnel in collecting and documentation
[25 empty] | Misidentification of germplasm | Misleading information | Include taxonomists during collecting. |  |  | Use molecular methods to verify identity. Invite taxonomists and other experts to verify identity of ambiguous materials. | GRU
Misidentification of germplasm
Misidentification of germplasm
Misidentification of germplasm
Misidentification of germplasm
Misidentification of germplasm
Misidentification of germplasm
Misidentification of germplasm
Misidentification of germplasm
Misidentification of germplasm
[25 empty] | Lack of simple collection protocol and documentation forms | Failure to capture diversity in field |  |  | Develop simple collecting procedures and forms. |  | GRU
Lack of simple collection protocol and documentation forms
Lack of simple collection protocol and documentation forms
Lack of simple collection protocol and documentation forms
Lack of simple collection protocol and documentation forms
Lack of simple collection protocol and documentation forms
Lack of simple collection protocol and documentation forms
Lack of simple collection protocol and documentation forms
Lack of simple collection protocol and documentation forms
Lack of simple collection protocol and documentation forms
[25 empty] | Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events | Loss of germplasm in habitat |  |  | Prioritize affected and high-diversity areas for collecting germplasm |  | GRU
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
Agricultural intensification, replacement of traditional varieties with modern ones, urbanization, land use change, and climatic events
[25 empty] | Strict country and international laws on access and use of germplasm | Poor access and use of germplasm in unexplored areas |  |  | Secure a Germplasm Acquisition Agreement between donor country and Centre to manage accessions under FAO conditions. | Arrange for unrestricted use with new leaders of donor countries. Acquire material through friendly 3rd party countries. Offer technical incentives. | GRU
Strict country and international laws on access and use of germplasm
Strict country and international laws on access and use of germplasm
Strict country and international laws on access and use of germplasm
Strict country and international laws on access and use of germplasm
Strict country and international laws on access and use of germplasm
Strict country and international laws on access and use of germplasm
Strict country and international laws on access and use of germplasm
Strict country and international laws on access and use of germplasm
Strict country and international laws on access and use of germplasm
[25 empty] | Breach of country and international treaties | Legal consequences. Damaged reputation and relationship | Training of all institute staff on intenationally agreed protocols, in consultation with Genebank and other Center authorities. |  | Follow national procedures of obtaining collecting permits, under relevant international agreements. • Collect in partnership with local PGR people. | Keep acquired material under restricted use and access, and seek de-restriction with donor country. | Center top mgt; new employees orientation; GRU
Breach of country and international treaties
Breach of country and international treaties
Breach of country and international treaties
Breach of country and international treaties
Breach of country and international treaties
Breach of country and international treaties
Breach of country and international treaties
Breach of country and international treaties
Breach of country and international treaties
[25 empty] | Ambiguous position of countries regarding international treaties | Poor access and use of germplasm in unexplored areas |  |  | Foster goodwill through PGR, pre-breeding, breeding and Treaty-related training-workshops, and incentivize donation. | Help build capacity of national bodies in germplasm collecting. | Center partnership and collaboration office, GRU
Ambiguous position of countries regarding international treaties
Ambiguous position of countries regarding international treaties
Ambiguous position of countries regarding international treaties
Ambiguous position of countries regarding international treaties
Ambiguous position of countries regarding international treaties
Ambiguous position of countries regarding international treaties
Ambiguous position of countries regarding international treaties
Ambiguous position of countries regarding international treaties
Ambiguous position of countries regarding international treaties
[25 empty] | Exposure to crime-related events during collection trips | Serious injuries or death due to assault, crossfire, abductions, etc. |  |  |  | Properly coordinating schedule of trips with LGU to finalize the best time for collecting | GRU
Exposure to crime-related events during collection trips
Exposure to crime-related events during collection trips
Exposure to crime-related events during collection trips
Exposure to crime-related events during collection trips
Exposure to crime-related events during collection trips
Exposure to crime-related events during collection trips
Exposure to crime-related events during collection trips
Exposure to crime-related events during collection trips
Exposure to crime-related events during collection trips
[25 empty] | Exposure to natural disasters during collection trips | Serious injuries or death |  |  |  | Arrange schedule to avoid typhoons | GRU
Exposure to natural disasters during collection trips
Exposure to natural disasters during collection trips
Exposure to natural disasters during collection trips
Exposure to natural disasters during collection trips
Exposure to natural disasters during collection trips
Exposure to natural disasters during collection trips
Exposure to natural disasters during collection trips
Exposure to natural disasters during collection trips
Exposure to natural disasters during collection trips
[25 empty] | Exposure to road hazards and poor travel conditions | Illness, serious injuries or death due to accidents or extreme exhaustion. |  |  |  | Planning of travel routes avoiding hazardous roads and conditions | GRU
[25 empty] | Personnel becoming lost or hurt due to unfamiliarity to place, customs, local dialects in area of collection | Serious injuries or death due to mistaken identity or offending local residents who might get angry. |  |  |  | Deploying well-versed or local collector who knows the local customs and dialect | GRU
[25 empty] | Exposure to dangerous animal bites, exotic diseases and viral infections that may be common to the collection site such as SARS, A(H1N1), malaria, dengue, measles, rabies, etc. | Illness, serious injuries or death due to infection. |  |  |  | Safeguarding staff by immunization vaccines, providing them with safety kits or access to doctors available in the area. | GRU
[24 empty] | Acquisition: Donation | Received foreign materials carry pests and diseases | Introduction of pest and diseases to host country |  |  | Strictly observe quarantine regulations. Keep from main storage areas until fully checked and decontaminated. Subject to hot water treatment. Grow and regenerate materials in screenhouse or away from large crop production areas of local farms. | Confine affected areas, discontinue planting of crop and eliminate other hosts in adjacent areas. | GRU; Germplasm Health unit
Received foreign materials carry pests and diseases
Received foreign materials carry pests and diseases
Received foreign materials carry pests and diseases
Received foreign materials carry pests and diseases
Received foreign materials carry pests and diseases
Received foreign materials carry pests and diseases
Received foreign materials carry pests and diseases
Received foreign materials carry pests and diseases
Received foreign materials carry pests and diseases
[25 empty] | Limited seed testing capability | Restricts international germplasm exchange |  | Develop testing and handling capability for pests and diseases of international importance. |  |  | GRU; Germplasm Health unit
Limited seed testing capability
Limited seed testing capability
Limited seed testing capability
Limited seed testing capability
Limited seed testing capability
Limited seed testing capability
Limited seed testing capability
Limited seed testing capability
Limited seed testing capability
[25 empty] | Reluctance to share germplasm due to IP rights | Restricts international germplasm exchange |  | Conduct training on benefits and limitations of IP rights. |  |  | GRU
Reluctance to share germplasm due to IP rights
Reluctance to share germplasm due to IP rights
Reluctance to share germplasm due to IP rights
Reluctance to share germplasm due to IP rights
Reluctance to share germplasm due to IP rights
Reluctance to share germplasm due to IP rights
Reluctance to share germplasm due to IP rights
Reluctance to share germplasm due to IP rights
Reluctance to share germplasm due to IP rights
[25 empty] | Working collections not duplicated in major genebanks | Failure to capture elite germplasm |  |  | Proactively conserve breeding materials. |  | GRU
Working collections not duplicated in major genebanks
Working collections not duplicated in major genebanks
Working collections not duplicated in major genebanks
Working collections not duplicated in major genebanks
Working collections not duplicated in major genebanks
Working collections not duplicated in major genebanks
Working collections not duplicated in major genebanks
Working collections not duplicated in major genebanks
Working collections not duplicated in major genebanks
[25 empty] | Donated seeds carrying seed-borne pests and other pathogens | Possible pest or disease infestation if unchecked |  |  |  | Fumigation of donated samples as soon as they arrive | GRU
[24 empty] | Conservation: Registration | Unverified passport and other data submitted | Incorrect or unreliable passport data, and subsequent reports |  |  | Verify passport information with donor. | Classify accessions as ‘tentative’ until standard characterization, etiology and DNA analysis establish their identity. | GRU
Unverified passport and other data submitted
Unverified passport and other data submitted
Unverified passport and other data submitted
Unverified passport and other data submitted
Unverified passport and other data submitted
Unverified passport and other data submitted
Unverified passport and other data submitted
Unverified passport and other data submitted
Unverified passport and other data submitted
[25 empty] | Received materials have low viability | Loss of germplasm |  |  | Obtain large amount of samples and handle properly. | Seed increase immediately. | GRU
Received materials have low viability
Received materials have low viability
Received materials have low viability
Received materials have low viability
Received materials have low viability
Received materials have low viability
Received materials have low viability
Received materials have low viability
Received materials have low viability
[24 empty] | Conservation: Sample Processing | Culling of perceived offtypes that are true components of original sample | Loss of genetic integrity | Assign handling of highly heterogenous samples to well-trained personnel. |  | Prepare seed file, panicle file and herbarium specimen of heterogenous samples. Keep putative offtypes until verified with new harvest. | Collect new seeds and panicles from donor, site or safety duplicates in other genebanks. | GRU
Culling of perceived offtypes that are true components of original sample
Culling of perceived offtypes that are true components of original sample
Culling of perceived offtypes that are true components of original sample
Culling of perceived offtypes that are true components of original sample
Culling of perceived offtypes that are true components of original sample
Culling of perceived offtypes that are true components of original sample
Culling of perceived offtypes that are true components of original sample
Culling of perceived offtypes that are true components of original sample
Culling of perceived offtypes that are true components of original sample
[25 empty] | Non-removal of damaged seeds hence reducing true viable sample size | Drift and loss of genetic integrity from presence of unremoved damaged/weak seeds. | Assign well-trained staff in seed cleaning |  | Strictly select for healthy seeds Include seed health testing during regular storage viability tests. | Collect new seeds and panicles from donor, site or safety duplicates in other genebanks. | GRU; Seed Health
Non-removal of damaged seeds hence reducing true viable sample size
Non-removal of damaged seeds hence reducing true viable sample size
Non-removal of damaged seeds hence reducing true viable sample size
Non-removal of damaged seeds hence reducing true viable sample size
Non-removal of damaged seeds hence reducing true viable sample size
Non-removal of damaged seeds hence reducing true viable sample size
Non-removal of damaged seeds hence reducing true viable sample size
Non-removal of damaged seeds hence reducing true viable sample size
Non-removal of damaged seeds hence reducing true viable sample size
[25 empty] | Inefficient fumigation | Drift and loss of genetic integrity from insect damage | Assign well-trained staff in seed processing |  | Apply fumigation at most effective doses. Include seed health testing during regular storage viability tests. | Collect new seeds and panicles from donor, site or safety duplicates in other genebanks. | GRU; Seed Health
Inefficient fumigation
Inefficient fumigation
Inefficient fumigation
Inefficient fumigation
Inefficient fumigation
Inefficient fumigation
Inefficient fumigation
Inefficient fumigation
Inefficient fumigation
[25 empty] | Lack of proper disposal procedures for contaminated plant materials | Dissemination of pests and diseases to new areas. |  |  | Develop and enforce proper disposal procedures for contaminated plant materials. | Confine affected areas, discontinue planting of crop and eliminate other hosts in adjacent areas. | GRU; Seed Health
Lack of proper disposal procedures for contaminated plant materials
Lack of proper disposal procedures for contaminated plant materials
Lack of proper disposal procedures for contaminated plant materials
Lack of proper disposal procedures for contaminated plant materials
Lack of proper disposal procedures for contaminated plant materials
Lack of proper disposal procedures for contaminated plant materials
Lack of proper disposal procedures for contaminated plant materials
Lack of proper disposal procedures for contaminated plant materials
Lack of proper disposal procedures for contaminated plant materials
[25 empty] | Mixture from unclean mechanical threshers and selection of hardy grains resistant to mechanical threshers | Loss of genetic integrity |  | If mechanical thresher is necessary, thoroughly clean equipment and collecting tray between samples. | Thresh and clean samples manually, and clean work table between samples. | Collect new seeds and panicles from donor, site or safety duplicates in other genebanks. | GRU
Mixture from unclean mechanical threshers and selection of hardy grains resistant to mechanical threshers
Mixture from unclean mechanical threshers and selection of hardy grains resistant to mechanical threshers
Mixture from unclean mechanical threshers and selection of hardy grains resistant to mechanical threshers
Mixture from unclean mechanical threshers and selection of hardy grains resistant to mechanical threshers
Mixture from unclean mechanical threshers and selection of hardy grains resistant to mechanical threshers
Mixture from unclean mechanical threshers and selection of hardy grains resistant to mechanical threshers
Mixture from unclean mechanical threshers and selection of hardy grains resistant to mechanical threshers
Mixture from unclean mechanical threshers and selection of hardy grains resistant to mechanical threshers
Mixture from unclean mechanical threshers and selection of hardy grains resistant to mechanical threshers
[25 empty] | Body parts coming in contact with hot components, moving parts, unguarded machines, and sharp objects during harvesting, threshing, oven drying or packaging of samples. | Scalds, burns, blisters, cuts, bruises, wounds and infection due to the above-mentioned injuries.
[25 empty] | Exposure to allergens (dust, trichomes, insect bites and other airborne irritants) from samples being processed | Allergies from insect bites, trichomes and dust and infection from scratching. |  |  |  | Provide prescribed PPEs and install air purifying equipment | GRU
[25 empty] | Improper posture due to prolonged sitting or standing | Injury from muscle pains and cramps (likelihood of muscle pain might be higher than cramps) evaluate it separately …
[25 empty] | Inadequate or improper illumination during seed cleaning | Eye strain, headache
[25 empty] | Exposure to microscopic particulates during reactivation of silica gel dessicant | Serious respiratory injury due to inhalation of particulates of silica gel dust.
[24 empty] | Conservation: Storage | Misplacement of packets back into storage tray during briefings to visitors | Loss or misplacement of germplasm | Restrict germplasm access to authorized staff. |  | Conduct regular and independent verification of location of accession, and update it on computerized database system. Make packet and tray labels highly visible. | Replace affected accessions with seeds from base set. Collect new seeds from donor, site or safety duplicates in other genebanks. | GRU
Misplacement of packets back into storage tray during briefings to visitors
Misplacement of packets back into storage tray during briefings to visitors
Misplacement of packets back into storage tray during briefings to visitors
Misplacement of packets back into storage tray during briefings to visitors
Misplacement of packets back into storage tray during briefings to visitors
Misplacement of packets back into storage tray during briefings to visitors
Misplacement of packets back into storage tray during briefings to visitors
Misplacement of packets back into storage tray during briefings to visitors
Misplacement of packets back into storage tray during briefings to visitors
[25 empty] | Underestimate of critical sample size | Loss of genetic integrity |  |  | Store excess base set stock (1500-6000 seeds) with due regard to expected decline in viability during storage. | Replace affected accessions with seeds from base set. Collect new seeds from donor, site or safety duplicates in other genebanks. | GRU
Underestimate of critical sample size
Underestimate of critical sample size
Underestimate of critical sample size
Underestimate of critical sample size
Underestimate of critical sample size
Underestimate of critical sample size
Underestimate of critical sample size
Underestimate of critical sample size
Underestimate of critical sample size
[25 empty] | Ineffective packaging material and method permeable to moisture, pest or pathogen | Reduction or loss of viability |  | Ensure sealing apparatus is working properly, and packaging area and technique are aseptic. | Use industry-standard packaging material and method that is impermeable to moisture, pest or pathogen. | Replace affected accessions with seeds from base set. Collect new seeds from donor, site or safety duplicates in other genebanks. | GRU
Ineffective packaging material and method permeable to moisture, pest or pathogen
Ineffective packaging material and method permeable to moisture, pest or pathogen
Ineffective packaging material and method permeable to moisture, pest or pathogen
Ineffective packaging material and method permeable to moisture, pest or pathogen
Ineffective packaging material and method permeable to moisture, pest or pathogen
Ineffective packaging material and method permeable to moisture, pest or pathogen
Ineffective packaging material and method permeable to moisture, pest or pathogen
Ineffective packaging material and method permeable to moisture, pest or pathogen
Ineffective packaging material and method permeable to moisture, pest or pathogen
[25 empty] | Safety duplication site is vulnerable to natural calamities | Inaccessible or loss of safety duplication |  | Full back-up in NCGRP, Fort Collins, Colorado. |  |  | GRU
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
Safety duplication site is vulnerable to natural calamities
[25 empty] | Changing policies, financial and technical capabilities of governments hosting safety duplication | Inaccessible or loss of safety duplication |  | Secondary full back-up in Svalbard, Norway. Partial back-up in another CGIAR center. Prepare a pull-out scheme in the event of instability in host country. |  |  | Center top mgt; SGRP; GRU
Changing policies, financial and technical capabilities of governments hosting safety duplication
Changing policies, financial and technical capabilities of governments hosting safety duplication
Changing policies, financial and technical capabilities of governments hosting safety duplication
Changing policies, financial and technical capabilities of governments hosting safety duplication
Changing policies, financial and technical capabilities of governments hosting safety duplication
Changing policies, financial and technical capabilities of governments hosting safety duplication
Changing policies, financial and technical capabilities of governments hosting safety duplication
Changing policies, financial and technical capabilities of governments hosting safety duplication
Changing policies, financial and technical capabilities of governments hosting safety duplication
[25 empty] | Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests) | Reduction or loss of viability |  |  |  | Plan for upgrade of facilities. Install an alarm system for open doors, and temperature/ humidity changes in the processing and storage areas. Regularly check and maintain cooling units and dehumidifiers. Multiply, carefully process and send accessions to international genebanks for safety duplication. | GRU
[25 empty] | Poor organization of storage trays, shelves and compartments | Loss or misplacement of germplasm
[25 empty] | Deterioration of facilities and equipment | Reduction or loss of seed viability |  |  |  | Pursue continual upgrading and expansion of field and laboratory equipment. | GRU
[25 empty] | Cold room malfunction | Reduction or loss of seed viability |  |  |  | Place hygrothermo-graphs that are connected to back-up power supply and alarm system. Provide the rooms with multiple compressors and dehumidifiers that are programmed for alternate operation.
[25 empty] | Power supply cut-off | Reduction or loss of seed viability
[25 empty] | Theft or vandalism | Loss of germplasm
[25 empty] | Exposure to falling jars or boxes while stocking seed samples for storage | Minor to serious injuries or death due to trauma caused by falling jars or boxes |  |  |  | Secure boxes and jars with railguards | GRU
[25 empty] | Exposure of personnel to extreme temperature changes during storage processes (stocking of samples in the cold chambers, etc.) or from being accidentally trapped in the cold rooms. | Illness due to thermal shock (from cold to hot) or hypothermia (from hot to cold; Thermal shock or hypothermia (is this possible to evaluate separately?).
[25 empty] | Exposure to sharp awns and trichomes during viability scoring | HS - Allergies from trichomes and infection from pinpricks caused by the sharp awns.
[24 empty] | Conservation: Testing | Human error in taking and encoding weight readings | Incorrect moisture content data | Assign well-trained staff |  | Computerize MC determination based on weight readings from two . | Conduct a third replicate if there is wide variation between two replicates. | GRU
[25 empty] | Defective weighing apparatus | Incorrect moisture content data |  | Quarterly calibrate weighing balance. |  |  | GRU
[25 empty] | Inefficient conduct of viability test and encoding | Overdue/backlog in viability test | Plan in advance and hire properly trained technicians and encoders. |  | Closely monitor and follow viability testing schedule | Prioritize specail and unique accessions. | GRU
[25 empty] | Human error in viability evaluation. | Incorrect viability score | Assign staff that are well trained on ISTA standards. |  | Determine viability from two replicates. | Conduct a third replicate if there is wide variation between two replicates. | GRU
[25 empty] | Dormancy | Incorrect viability score |  |  | Break dormancy. Optimize methods to break dormancy of recalcitrant types and wild species. |  | GRU
[25 empty] | Unsuitable viability testing procedure for special types of germplasm | Incorrect viability score |  |  | Request appropriate growing procedure from donor. Improve germination of problematic seed types. | Try germination on agar. | GRU
[25 empty] | Inappropriate viability testing interval | Loss of viability |  |  | Establish viability testing intervals for different seed types. | Replace with seeds from base set. Collect new seeds from donor, site or safety duplicates in other genebanks. | GRU
[25 empty] | Human error in seed health evaluation. | Pest incidence undetected | Assign staff that are well trained in International Seed Testing Association (ISTA) and US National Seed Health System protocols in seed health testing. Engage Center pathologists and virologists. |  | Determine seed health from two replicates. | Conduct a third replicate if there is wide variation between two replicates. | GRU; Seed Health
[25 empty] | Improper pest screening methods | Pest damage |  |  | Comply with quality standards held by center and/or country regulations. Develop improved methods to minimize errors in seed health laboratory techniques for detection of pathogens. | Replace with seeds from base set. Collect new seeds from donor, site or safety duplicates in other genebanks. | GRU
[25 empty] | Defective pest screening equipment | Pest damage |  | Periodically inspect pathology labs and calibrate equipment. |  |  | GRU
[25 empty] | Untrained personnel in transgene detection | Loss of genetic integrity of other accessions | Conduct regular training of staff in transgenic detection. |  |  | Replace with seeds from base set if available. Request or collect new seeds from donor or site or from well-conserved safety duplicates in other genebanks. | GRU
[25 empty] | Lack or improper determination of transgene presence | Inaccurate or wrong information regarding transgene presence |  |  | Use industry-standard transgene detection systems. |  | GRU
[25 empty] | Inadvertent spread of transgene in the collection | Loss of genetic integrity of other accessions | Designate a separate group of personnel for handling transgenic materials. | Designate a separate processing and storage rooms for handling and conserving transgenic materials. Assign experimental area for transgenics away from seed multiplication plots. | During registration, require a special declaration that seed samples contain no transgenes. Follow host country and center biosafety protocols to minimize accidental transfer of transgenes to non-transgenic accessions. | Test seeds of adjacent plots for transgene presence. Replace affected accessions with seeds from base set. Collect new seeds from donor, site or safety duplicates in other genebanks. | GRU
[24 empty] | Conservation: Regeneration | Poor field plot management | Loss of genetic integrity |  | Use standard large plot sizes to ensure minimal drift. | Follow standard procedures for plot management ensuring that at least 100 plants can be grown to maturity. | Replace affected accessions with seeds from base set. Collect new seeds from donor, site or safety duplicates in other genebanks. | GRU
Poor field plot management
Poor field plot management
Poor field plot management
Poor field plot management
Poor field plot management
Poor field plot management
Poor field plot management
Poor field plot management
Poor field plot management
[25 empty] | Misidentification of accessions | Loss of germplasm | Assign multiple staff in seed preparation, labelling, seed distribution in seed bed, and seedling distribution in field plots. |  | Double check seed and seedling labels against planting plant before and after distribution in seed bed and field plots. |  | GRU
Misidentification of accessions
Misidentification of accessions
Misidentification of accessions
Misidentification of accessions
Misidentification of accessions
Misidentification of accessions
Misidentification of accessions
Misidentification of accessions
Misidentification of accessions
[25 empty] | Mis-roguing of true components of original germplasm | Loss of genetic integrity | Assign handling of highly heterogenous samples to well-trained personnel. |  | Separate regeneration of highly heterogenous samples based on seed characteristisc of original samples. | Replace affected accessions with seeds from base set. Collect new seeds from donor, site or safety duplicates in other genebanks. | GRU
Mis-roguing of true components of original germplasm
Mis-roguing of true components of original germplasm
Mis-roguing of true components of original germplasm
Mis-roguing of true components of original germplasm
Mis-roguing of true components of original germplasm
Mis-roguing of true components of original germplasm
Mis-roguing of true components of original germplasm
Mis-roguing of true components of original germplasm
Mis-roguing of true components of original germplasm
[25 empty] | Differential pollen productivity of subtypes in highly heterogenous samples. | Loss of genetic integrity |  |  | Seperately harvest seeds from the different subtypes of the accession and pool them proportionally to constitute the sample for storage. | Replace affected accessions with seeds from base set. Collect new seeds from donor, site or safety duplicates in other genebanks. | GRU
Differential pollen productivity of subtypes in highly heterogenous samples.
Differential pollen productivity of subtypes in highly heterogenous samples.
Differential pollen productivity of subtypes in highly heterogenous samples.
Differential pollen productivity of subtypes in highly heterogenous samples.
Differential pollen productivity of subtypes in highly heterogenous samples.
Differential pollen productivity of subtypes in highly heterogenous samples.
Differential pollen productivity of subtypes in highly heterogenous samples.
Differential pollen productivity of subtypes in highly heterogenous samples.
Differential pollen productivity of subtypes in highly heterogenous samples.
[25 empty] | Cross pollination from other germplasm | Loss of genetic integrity |  | Set up regeneration of wild species inside a secure screenhouse. Consider installing pollen barriers in screenhouse. In the field, prevent pollination by alien pollen through proper isolation. | Use 30 cm x 30 cm spacing for photosensitive and high tillering accessions, and new materials. Intersperse plots with different species. If applicable, bag seed heads before pollen shedding. Use field plot layout that avoids potential risk of outcrossing with survivors of past plantings. | Replace affected accessions with seeds from base set. Collect new seeds from donor, site or safety duplicates in other genebanks. | GRU
Cross pollination from other germplasm
Cross pollination from other germplasm
Cross pollination from other germplasm
Cross pollination from other germplasm
Cross pollination from other germplasm
Cross pollination from other germplasm
Cross pollination from other germplasm
Cross pollination from other germplasm
Cross pollination from other germplasm
[25 empty] | Suboptimal pollination | Loss of genetic integrity |  | Provide pollination cages if necessary. | Use relevant pollinators to ensure pollination, minimize differential contribution of male gametes by artificial pollination, and ensure appropriate female-male pairing by isolation, manual pollination, etc. |  | GRU
Suboptimal pollination
Suboptimal pollination
Suboptimal pollination
Suboptimal pollination
Suboptimal pollination
Suboptimal pollination
Suboptimal pollination
Suboptimal pollination
Suboptimal pollination
[25 empty] | Poor quality of harvest for storage | Loss of genetic integrity |  |  | Harvest seeds at physiological maturity. Slow dry and blow seed before and after drying to remove stubble and unfilled and light grains. |  | GRU
Poor quality of harvest for storage
Poor quality of harvest for storage
Poor quality of harvest for storage
Poor quality of harvest for storage
Poor quality of harvest for storage
Poor quality of harvest for storage
Poor quality of harvest for storage
Poor quality of harvest for storage
Poor quality of harvest for storage
[25 empty] | Different regeneration environment from the site of origin | Genetic shift or loss of genetic integrity |  | Review geographical origin of germplasm and carry out regeneration in the same or similar environment or in controlled environments (e.g. greenhouses, screen cages, etc.) that meet the environmental requirements of the germplasm. | Grow different species under their optimal light requirements. |  | GRU
Different regeneration environment from the site of origin
Different regeneration environment from the site of origin
Different regeneration environment from the site of origin
Different regeneration environment from the site of origin
Different regeneration environment from the site of origin
Different regeneration environment from the site of origin
Different regeneration environment from the site of origin
Different regeneration environment from the site of origin
Different regeneration environment from the site of origin
[25 empty] | Inappropriate location of genebank for regeneration of photoperiod-sensitive materials | Failure to produce new seeds |  |  | Grow wild species and photoperiod-sensitive accessions during wet season. |  | GRU
Inappropriate location of genebank for regeneration of photoperiod-sensitive materials
Inappropriate location of genebank for regeneration of photoperiod-sensitive materials
Inappropriate location of genebank for regeneration of photoperiod-sensitive materials
Inappropriate location of genebank for regeneration of photoperiod-sensitive materials
Inappropriate location of genebank for regeneration of photoperiod-sensitive materials
Inappropriate location of genebank for regeneration of photoperiod-sensitive materials
Inappropriate location of genebank for regeneration of photoperiod-sensitive materials
Inappropriate location of genebank for regeneration of photoperiod-sensitive materials
Inappropriate location of genebank for regeneration of photoperiod-sensitive materials
[25 empty] | Escape of non-native species into environment | Invasion of host habitat | Regulate access to screenhouse and staff should change working clothes to minimize dispersal of seeds when they leave. | Restrict growing of wild species in pots with no holes inside a contained screenhouse with fine-mesh screens on all drainage canals. | After harvest, incinerate all remaining materials including the soil. | Confine affected areas, monitor for non-native wild species and eliminate them before reproductive stage. | GRU
Escape of non-native species into environment
Escape of non-native species into environment
Escape of non-native species into environment
Escape of non-native species into environment
Escape of non-native species into environment
Escape of non-native species into environment
Escape of non-native species into environment
Escape of non-native species into environment
Escape of non-native species into environment
[25 empty] | Endemic diseases from adjacent production areas | Loss of germplasm |  | Conduct regeneration in isolated areas away from production farms. |  |  | GRU
Endemic diseases from adjacent production areas
Endemic diseases from adjacent production areas
Endemic diseases from adjacent production areas
Endemic diseases from adjacent production areas
Endemic diseases from adjacent production areas
Endemic diseases from adjacent production areas
Endemic diseases from adjacent production areas
Endemic diseases from adjacent production areas
Endemic diseases from adjacent production areas
[25 empty] | Unavailability of pesticides to control major insect pests due to strict regulations | Loss of germplasm
Unavailability of pesticides to control major insect pests due to strict regulations
Unavailability of pesticides to control major insect pests due to strict regulations
Unavailability of pesticides to control major insect pests due to strict regulations
Unavailability of pesticides to control major insect pests due to strict regulations
Unavailability of pesticides to control major insect pests due to strict regulations
Unavailability of pesticides to control major insect pests due to strict regulations
Unavailability of pesticides to control major insect pests due to strict regulations
Unavailability of pesticides to control major insect pests due to strict regulations
Unavailability of pesticides to control major insect pests due to strict regulations
[25 empty] | Low germination of germplasm due to strong dormancy | Loss of germplasm |  |  | Conduct research on the physiology of seed dormancy and methods to break dormancy. Gather and integrate traditional knowledge for optimal regeneration of landraces and primitive. | Use tissue culture and embryo rescue to germinate recalcitrant accessions. Scrub seed of certain species with sand paper to relieve dormancy. | GRU
Low germination of germplasm due to strong dormancy
Low germination of germplasm due to strong dormancy
Low germination of germplasm due to strong dormancy
Low germination of germplasm due to strong dormancy
Low germination of germplasm due to strong dormancy
Low germination of germplasm due to strong dormancy
Low germination of germplasm due to strong dormancy
Low germination of germplasm due to strong dormancy
Low germination of germplasm due to strong dormancy
[24 empty] | Conservation: Characterization and Evaluation | Inefficient and erroneous data gathering and encoding | Backlog and inaccurate characterization data | Assign staff with adequate training in characterization following international standards. | Provide digital hand-held encoder. | Independently verify encoded data. Automate computing, updating and reporting of characterization data in database. |  | GRU
Inefficient and erroneous data gathering and encoding
Inefficient and erroneous data gathering and encoding
Inefficient and erroneous data gathering and encoding
Inefficient and erroneous data gathering and encoding
Inefficient and erroneous data gathering and encoding
Inefficient and erroneous data gathering and encoding
Inefficient and erroneous data gathering and encoding
Inefficient and erroneous data gathering and encoding
Inefficient and erroneous data gathering and encoding
[25 empty] | Descriptors that have no clear-cut correspondence to current international standard descriptors | No or limited usefulness of characterization data |  |  | Use updated descriptors and provide references for all measurements and classifications. | Re-characterize accessions for problematic traits using current international standard descriptors. | GRU
Descriptors that have no clear-cut correspondence to current international standard descriptors
Descriptors that have no clear-cut correspondence to current international standard descriptors
Descriptors that have no clear-cut correspondence to current international standard descriptors
Descriptors that have no clear-cut correspondence to current international standard descriptors
Descriptors that have no clear-cut correspondence to current international standard descriptors
Descriptors that have no clear-cut correspondence to current international standard descriptors
Descriptors that have no clear-cut correspondence to current international standard descriptors
Descriptors that have no clear-cut correspondence to current international standard descriptors
Descriptors that have no clear-cut correspondence to current international standard descriptors
[25 empty] | Limited text-based description | Incomplete and inaccurate morphological description |  |  | Include images (600-800 pixels) of key plant parts accompanied with standard color guide eg. Mansell colors. |  | GRU
Limited text-based description
Limited text-based description
Limited text-based description
Limited text-based description
Limited text-based description
Limited text-based description
Limited text-based description
Limited text-based description
Limited text-based description
[25 empty] | Lack of diversity assessment of collection | Unknown level of breadth, duplication and gaps in collection, and conservation of unnecessary duplicates |  |  | Conduct molecular profiling and diversity analysis | Determine a set of core collection and begin eliminating redundant duplicates of the core materials. | GRU
Lack of diversity assessment of collection
Lack of diversity assessment of collection
Lack of diversity assessment of collection
Lack of diversity assessment of collection
Lack of diversity assessment of collection
Lack of diversity assessment of collection
Lack of diversity assessment of collection
Lack of diversity assessment of collection
Lack of diversity assessment of collection
[24 empty] | Distribution: Policies | Lack of knowledge or negligence on seed exchange Protocol and International Treaty | Distribution without accompanying MTA. Inadvertent distribution of restricted germplasm (e.g. Non-MLS materials). Wrong information on the exchange status (MLS) of the germplasm. | Conduct regular update on international agreements concerning germplasm exchange. |  | Implement a clearance sheet for germplasm distribution ensuring appropriate MTA and other documents and approval of personnel concerned are obtained before release. | Immediately send correct documents and information to recipient of germplasm, including acknowledgment receipt and agreement forms to be completed and returned. | GRU; Plant Breeding; Training
Lack of knowledge or negligence on seed exchange Protocol and International Treaty
Lack of knowledge or negligence on seed exchange Protocol and International Treaty
Lack of knowledge or negligence on seed exchange Protocol and International Treaty
Lack of knowledge or negligence on seed exchange Protocol and International Treaty
Lack of knowledge or negligence on seed exchange Protocol and International Treaty
Lack of knowledge or negligence on seed exchange Protocol and International Treaty
Lack of knowledge or negligence on seed exchange Protocol and International Treaty
Lack of knowledge or negligence on seed exchange Protocol and International Treaty
Lack of knowledge or negligence on seed exchange Protocol and International Treaty
[25 empty] | Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm | Restrictions on future access and use of germplasm |  |  | Distribute accessions under a standard FAO-CGIAR MTA for “designated” germplasm, and for Center-created "non-designated" material developed in collaboration with FAO and other CGIAR Center, with a clause on the right of the Center to take legal action in case of violation of the MTA, upon recipient's agreement to MTA conditions. | Send a notice to patent and PVP offices about status of germplasm materials in question. File legal suit against violators and prohibit their access to IT germplasm. | GRU; Center Mgt; FAO
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
Recipients of “designated” germplasm or “non-designated” germplasm attempt to claim IP rights over the germplasm
[25 empty] | Non-compliance with phytosanitary regulations | Germplasm distributed from genebank carry diseases or pest contamination. |  |  | Seed Health Unit tests materials for bacterial and fungal diseases according to the phytosanitary standards of the importing country. | Immediately send disease and pest management procedures to recipients of germplasm. | GRU; Seed Health Unit
Non-compliance with phytosanitary regulations
Non-compliance with phytosanitary regulations
Non-compliance with phytosanitary regulations
Non-compliance with phytosanitary regulations
Non-compliance with phytosanitary regulations
Non-compliance with phytosanitary regulations
Non-compliance with phytosanitary regulations
Non-compliance with phytosanitary regulations
Non-compliance with phytosanitary regulations
[24 empty] | Distribution: Seed or Explant Preparation | Misclassification and wrong characterization and seed stocks data | Delayed identification and preparation of requested germplasm | Conduct regular training on seed characterization. |  | Check characterization data. Include evaluation data that relate to needs of different users. | Acknowledge receipt of seed request. If there is reasonable doubt on identity and availability of requested germplasm, notify requester of possible delay of delivery. | GRU, Library, Communications Office
Misclassification and wrong characterization and seed stocks data
Misclassification and wrong characterization and seed stocks data
Misclassification and wrong characterization and seed stocks data
Misclassification and wrong characterization and seed stocks data
Misclassification and wrong characterization and seed stocks data
Misclassification and wrong characterization and seed stocks data
Misclassification and wrong characterization and seed stocks data
Misclassification and wrong characterization and seed stocks data
Misclassification and wrong characterization and seed stocks data
[25 empty] | Inefficient and slow processing of requests for samples. | Dissatisfied recipients of germplasm | Dedicate personnel to serving seed requests. |  | Keep files of relevant country and international quarantine documents . |  | GRU; Seed Health
Inefficient and slow processing of requests for samples.
Inefficient and slow processing of requests for samples.
Inefficient and slow processing of requests for samples.
Inefficient and slow processing of requests for samples.
Inefficient and slow processing of requests for samples.
Inefficient and slow processing of requests for samples.
Inefficient and slow processing of requests for samples.
Inefficient and slow processing of requests for samples.
Inefficient and slow processing of requests for samples.
[25 empty] | Errors in preparing or labeling samples | Wrong germplasm distributed by the genebank |  |  | Adopt barcoding and closely adhere to seed distribution protocol. | Immediately send correct germplasm and instructions on disposing received wrong germplasm. | GRU
Errors in preparing or labeling samples
Errors in preparing or labeling samples
Errors in preparing or labeling samples
Errors in preparing or labeling samples
Errors in preparing or labeling samples
Errors in preparing or labeling samples
Errors in preparing or labeling samples
Errors in preparing or labeling samples
Errors in preparing or labeling samples
[25 empty] | Insufficient seed stock for distribution | Delay in serving seed request |  |  | Keep a minimum of 1,500-2,000 seeds per accession in the active collection. Incorporate alerts in the computerized seed stock control system for low inventory. Keep plenty of popular genetic stocks and RILs in the active set as well as their DNA samples if available. | Conduct seed mutliplication of the accessions and notify requestor of expected date of availability. Make an agreement with requestor on funding and schedule of seed increase, if Center cannot immediately meet request. | GRU
Insufficient seed stock for distribution
Insufficient seed stock for distribution
Insufficient seed stock for distribution
Insufficient seed stock for distribution
Insufficient seed stock for distribution
Insufficient seed stock for distribution
Insufficient seed stock for distribution
Insufficient seed stock for distribution
Insufficient seed stock for distribution
[24 empty] | Distribution: Dispatch | Germplasm distributed with low viability | Dissatisfied recipients of germplasm |  |  | Conduct research on nature of dormancy and methods to break dormancy. Include a protocol on how to grow the particular material in every shipment, including breaking dormancy methods. | Immediately verify viability of seed batch, rejuvenate if necessary, and send highly viable seed to requestor if still needed. | GRU
Germplasm distributed with low viability
Germplasm distributed with low viability
Germplasm distributed with low viability
Germplasm distributed with low viability
Germplasm distributed with low viability
Germplasm distributed with low viability
Germplasm distributed with low viability
Germplasm distributed with low viability
Germplasm distributed with low viability
[25 empty] | Loss of documentation | Loss of important information about germplasm |  |  | Include copies of documentation inside shipping boxes. |  | GRU
Loss of documentation
Loss of documentation
Loss of documentation
Loss of documentation
Loss of documentation
Loss of documentation
Loss of documentation
Loss of documentation
Loss of documentation
[25 empty] | Unfavorable conditions during transport | Delay in delivery , reduction of viability or loss of materials |  |  | Use packing materials that can withstand unfavorable conditions. Choose express delivery and under dry-ice if available with reliable shipping services and tracking system. | If route and time taken by material are unreasonably extended, resend new seeds using an alternative courier. | GRU
Unfavorable conditions during transport
Unfavorable conditions during transport
Unfavorable conditions during transport
Unfavorable conditions during transport
Unfavorable conditions during transport
Unfavorable conditions during transport
Unfavorable conditions during transport
Unfavorable conditions during transport
Unfavorable conditions during transport
[24 empty] | Information Management and Dissemination: Labelling | Fading of labels and mislabelling of new bags and other containers for the germplasm accession | Wrong information on germplasm identity and inventory |  |  | Place fade-resistant, computer-generated labels and barcodes inside and outside all containers. Scan barcode labels twice on seeds and trays to prevent miscans, and then physically count entries on trays. | Verifiy identity with donor, records and DNA fingerprinting. | GRU
Fading of labels and mislabelling of new bags and other containers for the germplasm accession
Fading of labels and mislabelling of new bags and other containers for the germplasm accession
Fading of labels and mislabelling of new bags and other containers for the germplasm accession
Fading of labels and mislabelling of new bags and other containers for the germplasm accession
Fading of labels and mislabelling of new bags and other containers for the germplasm accession
Fading of labels and mislabelling of new bags and other containers for the germplasm accession
Fading of labels and mislabelling of new bags and other containers for the germplasm accession
Fading of labels and mislabelling of new bags and other containers for the germplasm accession
Fading of labels and mislabelling of new bags and other containers for the germplasm accession
[25 empty] | Misplacement of labels as seeds are laid out for drying | Loss of accessions | Assign handling to well trained personnel. Place labels carefully under the seeds to minimize errors. |  |  | Replace affected accessions with seeds from base set. Collect new seeds from donor, site or safety duplicates in other genebanks. | GRU
Misplacement of labels as seeds are laid out for drying
Misplacement of labels as seeds are laid out for drying
Misplacement of labels as seeds are laid out for drying
Misplacement of labels as seeds are laid out for drying
Misplacement of labels as seeds are laid out for drying
Misplacement of labels as seeds are laid out for drying
Misplacement of labels as seeds are laid out for drying
Misplacement of labels as seeds are laid out for drying
Misplacement of labels as seeds are laid out for drying
[24 empty] | Information Management and Dissemination: Data Handling | Inefficient recording and database management | Backlog and inaccurate characterization data |  |  | Use GRU Database System and submit new data to SINGER every month. Bind hard copies of data in books. |  | GRU, Information Technology Unit
Inefficient recording and database management
Inefficient recording and database management
Inefficient recording and database management
Inefficient recording and database management
Inefficient recording and database management
Inefficient recording and database management
Inefficient recording and database management
Inefficient recording and database management
Inefficient recording and database management
[25 empty] | Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation) | Loss or inaccessibility of information |  |  | Use GRU Database System and archive original data sheets. Integrate genebank operations, distribution records, and seed exchange policy databases. | Regularly monitor data handling and encode stray data. | GRU, Information Technology Unit
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
Mishandling of information and disorganized data sets (e.g. information system, field/ lab observation)
[25 empty] | Improper recording of moisture content, seed inventory, viability, storage location, and characterization data. | Inaccurate or wrong information |  |  | Independently verify encoded data. Automate computing, updating and reporting of moisture content, seed inventory, viability, storage location, and characterization data in database. Provide decision-making tools in the database for various genebanking operations. | Re-encode inventory and viability data from data sheets if reliable, otherwise repeat inventory and viability tests. | GRU
Improper recording of moisture content, seed inventory, viability, storage location, and characterization data.
Improper recording of moisture content, seed inventory, viability, storage location, and characterization data.
Improper recording of moisture content, seed inventory, viability, storage location, and characterization data.
Improper recording of moisture content, seed inventory, viability, storage location, and characterization data.
Improper recording of moisture content, seed inventory, viability, storage location, and characterization data.
Improper recording of moisture content, seed inventory, viability, storage location, and characterization data.
Improper recording of moisture content, seed inventory, viability, storage location, and characterization data.
Improper recording of moisture content, seed inventory, viability, storage location, and characterization data.
Improper recording of moisture content, seed inventory, viability, storage location, and characterization data.
[24 empty] | Information Management and Dissemination: Back-up | Lack of secure back-up | Loss of genebank data |  | Transfer new data on CD or tape in two central databases in separate buildings. Store also in secure, passport-regulated cyberspace. | Produce photocopy and electronic copy of original data sheets. Use automatic back-up after each session in workstation. Make daily incremental back-ups and weakly full back-ups. | Retrieve data from back-up electronic copies and /or paper records if available. | GRU, Information Technology Unit
Lack of secure back-up
Lack of secure back-up
Lack of secure back-up
Lack of secure back-up
Lack of secure back-up
Lack of secure back-up
Lack of secure back-up
Lack of secure back-up
Lack of secure back-up
[24 empty] | Information Management and Dissemination: Data Quality | Inaccurate location of collecting sites | Misrepresentation of ecogeographic distribution |  |  | Use GIS in collecting for easy integration in the global database system. |  | GRU
Inaccurate location of collecting sites
Inaccurate location of collecting sites
Inaccurate location of collecting sites
Inaccurate location of collecting sites
Inaccurate location of collecting sites
Inaccurate location of collecting sites
Inaccurate location of collecting sites
Inaccurate location of collecting sites
Inaccurate location of collecting sites
[25 empty] | Inadequate information about important traits of accessions. | Low interest and utilization of germplasm |  |  | Collect data on important traits. Include desirable information from various sources. |  | GRU
Inadequate information about important traits of accessions.
Inadequate information about important traits of accessions.
Inadequate information about important traits of accessions.
Inadequate information about important traits of accessions.
Inadequate information about important traits of accessions.
Inadequate information about important traits of accessions.
Inadequate information about important traits of accessions.
Inadequate information about important traits of accessions.
Inadequate information about important traits of accessions.
[25 empty] | Human error in data gathering | Erroneous data |  | Use hand-held pocket PCs in field data gathering. | Check data integrity with SQL commands to catch out-of-line data. |  | GRU
Human error in data gathering
Human error in data gathering
Human error in data gathering
Human error in data gathering
Human error in data gathering
Human error in data gathering
Human error in data gathering
Human error in data gathering
Human error in data gathering
[25 empty] | Important data and information remain in unuseful form. | Low level of utilization of germplasm and information. |  |  | Disseminate relevant information about germplasm through germplasm catalogs, newsletters, journals, bulletins, and operation manuals in print and cyber media. | Provide on-demand technical assistance for special data and information search about germplasm. | GRU, Library, Communications Office
Important data and information remain in unuseful form.
Important data and information remain in unuseful form.
Important data and information remain in unuseful form.
Important data and information remain in unuseful form.
Important data and information remain in unuseful form.
Important data and information remain in unuseful form.
Important data and information remain in unuseful form.
Important data and information remain in unuseful form.
Important data and information remain in unuseful form.
[24 empty] | Information Management and Dissemination: Data Sharing | Slow availability of evaluation data for international users | Low interest and utilization of germplasm |  | Computerize and harmonize database with global system. | Immediately submit evaluation data into international databases. |  | GRU
Slow availability of evaluation data for international users
Slow availability of evaluation data for international users
Slow availability of evaluation data for international users
Slow availability of evaluation data for international users
Slow availability of evaluation data for international users
Slow availability of evaluation data for international users
Slow availability of evaluation data for international users
Slow availability of evaluation data for international users
Slow availability of evaluation data for international users
[25 empty] | Limited ICT capability; server, network and IT related problems | Lack or poor accessibility of germplasm and important data to potential users | Engage a competent data curator to document decades of evaluation data in a centralized database system. | Use stable software and hardware and engage full technical support from Information Technology Unit. Change computers every 5 years. Upgrade memory and operating system every year. | Regulate software installation and downloading. Restrict use of computer to authorized personnel. | Provide information request menu on the webpage and serve requests by digging print and/or electronic records. | GRU, Information Technology Unit
Limited ICT capability; server, network and IT related problems
Limited ICT capability; server, network and IT related problems
Limited ICT capability; server, network and IT related problems
Limited ICT capability; server, network and IT related problems
Limited ICT capability; server, network and IT related problems
Limited ICT capability; server, network and IT related problems
Limited ICT capability; server, network and IT related problems
Limited ICT capability; server, network and IT related problems
Limited ICT capability; server, network and IT related problems
[25 empty] | Malfunctioning equipment, hardware and software problems, and power interruption | Failure to update data by genebank staff and damage to computerized database system |  | Install redundant UPS units and hot-swappable battery packages. Enforce automatic start-up of generator within 30 seconds. Use alternating 2 power-supplies connected to the same server. | Enable immediate notification of 2 staff at work and home phones in case of database-related problems. Back up data weekly to 2 tapes/CDs, 1 kept in Center, the other in staff’s home for 1 year and later in the international data hub. |  | GRU
Malfunctioning equipment, hardware and software problems, and power interruption
Malfunctioning equipment, hardware and software problems, and power interruption
Malfunctioning equipment, hardware and software problems, and power interruption
Malfunctioning equipment, hardware and software problems, and power interruption
Malfunctioning equipment, hardware and software problems, and power interruption
Malfunctioning equipment, hardware and software problems, and power interruption
Malfunctioning equipment, hardware and software problems, and power interruption
Malfunctioning equipment, hardware and software problems, and power interruption
Malfunctioning equipment, hardware and software problems, and power interruption
[24 empty] | Infrastructure / Physical Facility: Functionality | Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests) | Reduction or loss of viability |  | Install an alarm system for open doors, and temperature/ humidity changes in the processing and storage areas. | Regularly check and maintain cooling units and dehumidifiers. | Multiply, carefully process and send accessions to better genebanks and/or Svalbard for safety back-up. | GRU, Physical Plant
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
Storage conditions at genebank not suitable (temperature, humidity, light conditions, exposure to contaminating organisms, pests)
[25 empty] | Poor organization of storage trays, shelves and compartments | Loss or misplacement of germplasm |  | Rationalize arrangement of storage trays, shelves, and compartments. | Develop a simple labeling system for the storage space units. Conduct regular and independent verification of location of accession, and update it on computerized database system. |  | GRU
Poor organization of storage trays, shelves and compartments
Poor organization of storage trays, shelves and compartments
Poor organization of storage trays, shelves and compartments
Poor organization of storage trays, shelves and compartments
Poor organization of storage trays, shelves and compartments
Poor organization of storage trays, shelves and compartments
Poor organization of storage trays, shelves and compartments
Poor organization of storage trays, shelves and compartments
Poor organization of storage trays, shelves and compartments
[25 empty] | Deterioration of facilities and equipment | Reduction or loss of seed viability |  | Pursue continual upgrading and expansion of field and laboratory equipment, etc. |  |  | GRU
Deterioration of facilities and equipment
Deterioration of facilities and equipment
Deterioration of facilities and equipment
Deterioration of facilities and equipment
Deterioration of facilities and equipment
Deterioration of facilities and equipment
Deterioration of facilities and equipment
Deterioration of facilities and equipment
Deterioration of facilities and equipment
[25 empty] | Cold room malfunction | Reduction or loss of seed viability |  | Place hygrothermographs that are connected to back-up power supply and alarm system. Provide the rooms with multiple compressors and dehumidifiers that are programmed for alternate operation. |  |  | GRU, Physical Plant
Cold room malfunction
Cold room malfunction
Cold room malfunction
Cold room malfunction
Cold room malfunction
Cold room malfunction
Cold room malfunction
Cold room malfunction
Cold room malfunction
[24 empty] | Infrastructure / Physical Facility: Security | Power supply cut-off | Reduction or loss of viability |  | Install, regularly check, and maintain an emergency electrical generator for back-up power to the storage rooms, essential genebank lighting, monitoring devices, and access locks during electrical power failures. |  |  | GRU, Physical Plant
Power supply cut-off
Power supply cut-off
Power supply cut-off
Power supply cut-off
Power supply cut-off
Power supply cut-off
Power supply cut-off
Power supply cut-off
Power supply cut-off
[25 empty] | Theft or vandalism | Loss of germplasm |  | Place the building under 24-hr perimeter security surveillance. Link the alarm system by optical fiber with security office and police. Install double locks in sensitive areas and closed-circuit camera monitoring by guards. Install sensors for door contacts, glass breaks and unusual motion outside work hours. | Restrict access to genebank facilitites to authorized personnel with assigned badge and PIN code for access. Conduct background check on personnel who will use facility. Regularly brief security guards on the safety and security protocols of the genebanks. |  | GRU, Physical Plant, Security
Theft or vandalism
Theft or vandalism
Theft or vandalism
Theft or vandalism
Theft or vandalism
Theft or vandalism
Theft or vandalism
Theft or vandalism
Theft or vandalism
[25 empty] | Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire | Reduction or loss of viability | Assign personnel from genebank unit and security office for 24/7 watch of the facility. | Design and construct building according to safety, environmental and artillery protection, and earthquake proof standards. Install fire and gas alarm systems. Provide fire isolation doors, fire extinguishers, and doors than can open from inside cold chambers to prevent personnel getting trapped. | Conduct periodic maintenance checks and inspect genebank during heavy rains and earthquakes for leaks in the cold and drying rooms. Periodically check fire safety checks. |  | GRU
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
Environmental risks/weather elements, earthquakes, other catastrophic events (civil war,…), and fire
[24 empty] | Personnel and Support Services: Personnel | Inadequate complement of technical staff | Inefficient operations | Hire at least one highly qualified technician each to manage seed viability test, seed drying and moisture test, seed health test, characterization and regeneration, data management, and seed distribution. For an active collection with research and development needs, hire a scientist to take charge of planning, research and analysis, a technician to take charge of daily operation of the laboratory, laboratory assistants for seed cleaning, seed processing and seed packaging, and field workers for seeding, field-layout, screenhouse and field maintenance and harvesting. |  |  |  | GRU
Inadequate complement of technical staff
Inadequate complement of technical staff
Inadequate complement of technical staff
Inadequate complement of technical staff
Inadequate complement of technical staff
Inadequate complement of technical staff
Inadequate complement of technical staff
Inadequate complement of technical staff
Inadequate complement of technical staff
[25 empty] | Incompetent staff | Inefficient operations | Hire researchers with advanced degrees in plant physiology/genetics. Hire laboratory technicians with a background in plant science. Hire laboratory assistants with training in basic botany. Provide 1-2 weeks intensive on-site training for each new staff member on standardized laboratory and field protocols, followed by close supervision for as long as needed. |  |  |  | GRU
Incompetent staff
Incompetent staff
Incompetent staff
Incompetent staff
Incompetent staff
Incompetent staff
Incompetent staff
Incompetent staff
Incompetent staff
[24 empty] | Personnel and Support Services: Working environment | Routine tasks and uncompetitive remuneration | Fast staff turnover | Rotate work assignments as much as possible or assigning special projects to technicians. Educate workers on the mission of the facility to boost morale and establish a research-oriented approach to work. |  |  |  | GRU
Routine tasks and uncompetitive remuneration
Routine tasks and uncompetitive remuneration
Routine tasks and uncompetitive remuneration
Routine tasks and uncompetitive remuneration
Routine tasks and uncompetitive remuneration
Routine tasks and uncompetitive remuneration
Routine tasks and uncompetitive remuneration
Routine tasks and uncompetitive remuneration
Routine tasks and uncompetitive remuneration
[25 empty] | Exposure to occupational hazards | Reduced manpower capability |  |  | Protect staff members from pesticide exposure, for example, by spraying during weekends. |  | GRU, Pest Control unit
Exposure to occupational hazards
Exposure to occupational hazards
Exposure to occupational hazards
Exposure to occupational hazards
Exposure to occupational hazards
Exposure to occupational hazards
Exposure to occupational hazards
Exposure to occupational hazards
Exposure to occupational hazards
[25 empty] | ergonomics/functionality of laboratory furnitures (design flaws, equipment bought not to specification, etc) | Use of equipment or furniture not maximized or with limitations. |  |  |  | Plan and justify the purchase of equipment based on right specifications. | GRU
[24 empty] | Personnel and Support Services: Support Services | Inefficient human resources services | Delayed hiring of required manpower |  |  | Review and streamline hiring/recruitment protocol. |  | HR
Inefficient human resources services
Inefficient human resources services
Inefficient human resources services
Inefficient human resources services
Inefficient human resources services
Inefficient human resources services
Inefficient human resources services
Inefficient human resources services
Inefficient human resources services
[25 empty] | Inefficient purchasing and repair services | Delayed delivery/repair of required supplies and equipment |  |  | Review purchasing protocol to speed up requisition process. Keep spare parts for crucial pieces of equipment in stock (specially the ones not locally available), as a risk mitigation procedure (filters, batteries, lamps, fuses, sealing devices) | Tap equipment and supplies of partner organizations, for a fee if required, pending delivery of ordered equipment and supplies. | GRU
Inefficient purchasing and repair services
Inefficient purchasing and repair services
Inefficient purchasing and repair services
Inefficient purchasing and repair services
Inefficient purchasing and repair services
Inefficient purchasing and repair services
Inefficient purchasing and repair services
Inefficient purchasing and repair services
Inefficient purchasing and repair services
[25 empty] | Assigning manpower that are not trained for genebank work | Backlog or work delay due to inexpertise or inexperience
[24 empty] | Personnel and Support Services: Financial | High cost of genebank operations | Loss of donor and user support |  |  | Closely follow and seize funding opportunities with The Global Crop Diversity Trust and other funding donors. | Charge shipping fees to recipients of germplasm especially the private sector and well-funded public organizations. | GRU; Center mgt
High cost of genebank operations
High cost of genebank operations
High cost of genebank operations
High cost of genebank operations
High cost of genebank operations
High cost of genebank operations
High cost of genebank operations
High cost of genebank operations
High cost of genebank operations
[25 empty] | Late release of project funds | Threat of manpower reduction, delayed activities or backlogs. |  |  |  | Package the projects/studies to be able to get external project funding | GRU
0
0
0
0
A27
A28
A29
A30